{"text_format":"1","workbook":"xlsx","n_sheets":2,"sheets":["Sheet1","Sheet2"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":42,"n_cols":38,"rows_kept":42,"cut":false,"hidden":false,"merged":[[1,10,1,16],[1,17,1,23],[1,24,1,30],[1,31,1,37]]}
[]
[null,null,"Project Start Date:","2025-11-06",null,null,null,null,null,null,"Week 1",null,null,null,null,null,null,"Week 2",null,null,null,null,null,null,"Week 3",null,null,null,null,null,null,"Week 4"]
[null,null,"Project Name:","IDP Group 212",null,null,null,null,"Week starting",null,{"$f":"D2","v":"2025-11-06"},{"$f":"K3+1","v":"2025-11-07"},{"$f":"L3+1","v":"2025-11-08"},"2025-11-09","2025-11-10","2025-11-11",{"$f":"P3+1","v":"2025-11-12"},"2025-11-13",{"$f":"R3+1","v":"2025-11-14"},"2025-11-15","2025-11-16","2025-11-17","2025-11-18",{"$f":"W3+1","v":"2025-11-19"},{"$f":"X3+1","v":"2025-11-20"},{"$f":"Y3+1","v":"2025-11-21"},"2025-11-22","2025-11-23","2025-11-24",{"$f":"AC3+1","v":"2025-11-25"},"2025-11-26",{"$f":"AE3+1","v":"2025-11-27"},"2025-11-28",{"$f":"AG3+1","v":"2025-11-29"},{"$f":"AH3+1","v":"2025-11-30"},"2025-12-01",{"$f":"AJ3+1","v":"2025-12-02"},{"$f":"AK3+1","v":"2025-12-03"}]
[null,"#","Activity","Assigned to","Start ","End","Working Days","Status","%Done"]
[null,1,"Final IDP competition","Sam, Shuhan, Vittal, Jaya, Serena, Scott","2025-11-06","2025-12-02",{"$f":"IF(F5=\"\",\"\",NETWORKDAYS(E5,F5))","v":19},"In progress",0.15,null,{"$f":"IF(K$3=$F5,\"u\",\"\")","v":""},"","","","","","","","","",{"$f":"IF(U$3=$F5,\"u\",\"\")","v":""},"","","","","","","","","",{"$f":"IF(AE$3=$F5,\"u\",\"\")","v":""},"","","","","","u",""]
[null,2,"Deliveribles for Progress meeting 2","Shuhan, Vittal, Jaya, Scott, Sam, Serena","2025-11-12","2025-11-18",{"$f":"IF(F6=\"\",\"\",NETWORKDAYS(E6,F6))","v":5},"Complete",1,null,"","","","","","","","","","","","","u","","","","","","","","","","","","","","",""]
[null,3,"Deliveribles for Progress meeting 3","Shuhan, Vittal, Jaya, Scott, Sam, Serena","2025-11-18","2025-11-25",6,"In progress",0.3,null,"","","","","","","","","","","","","","","","","","","","u","","","","","","","",""]
[null,4,"Deliveribles for Progress meeting 4","Shuhan, Vittal, Jaya, Scott, Sam, Serena","2025-11-25","2025-12-02",6,"In progress",0,null,{"$f":"IF(K$3=$F8,\"u\",\"\")","v":""},{"$f":"IF(L$3=$F8,\"u\",\"\")","v":""},"","","","","","","","","","","","","","","","","","","","","","","","","u",""]
[null,5,"Working code for line tracking","Sam, Serena","2025-11-11","2025-11-17",5,"Complete",1,null,"","","","","","","","","","","","u","","","","","","","","","","","","","","","",""]
[null,6,"Chassis V1","Scott","2025-11-10","2025-11-13",4,"Complete",1,null,"","","","","","","","u","","","","","","","","","","","","","","","","","","","",""]
[null,7,"Chassis V2","Scott","2025-11-13","2025-11-14",{"$f":"IF(F11=\"\",\"\",NETWORKDAYS(E11,F11))","v":2},"Complete",1]
[null,8,"Chassis V3","Scott","2025-11-14","2025-11-19",4,"In progress",0.85]
[null,9,"Chassis Grabber Integration","Scott","2025-11-19","2025-11-24",null,"Not started ",0]
[null,10,"Schematic design","Shuhan","2025-11-10","2025-11-17",6,"Complete",1,null,"","","","","","","","","","","","u","","","","","","","","","","","","","","","",""]
[null,11,"Read sensor specification, carry out physical testing to help the team decide which sensors to use and how to use them.","Shuhan, Vittal","2025-11-06","2025-11-14",7,"Complete",1,null,"","","","","","","","","u","","","","","","","","","","","","","","","","","","",""]
[null,12,"Keep working area tidy","Shuhan, Vittal, Jaya, Scott, Sam, Serena","2025-11-06","2025-12-02",19,"Blocked",0,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","u",""]
[null,13,"Protoboard physical layout design","Shuhan","2025-11-12","2025-11-14",3,"Complete",1,null,"","","","","","","","","u","","","","",{"$f":"IF(X$3=$F17,\"u\",\"\")","v":""},"","","","","","","","","","","","","",""]
[null,14,"Soldering","Shuhan, Vittal","2025-11-14","2025-11-14",1,"Complete",1,null,"","","","","","","","","u","","","","","","","","","","","","","","","","","","",""]
[null,15,"design & model grabber","Jaya","2025-11-13","2025-11-20",6,"In progress",0.6,null,"","","","","","","","","","","","","","","u","","","","","","","","","","","","",""]
[null,16,"Full structure of code","Sam","2025-11-18","2025-11-21",4,"In progress",0.1,null,"","","","","","","","","","","","","","","","u","","","","","","","","","","","",""]
[null,17,"First version of working robot",null,"2025-11-18","2025-11-26",7,"In progress",0.2,null,"","","","","","","","","","","","","","","","","","","","","u","","","","","","",""]
[null,null,null,null,null,null,"",null,null,null,{"$f":"IF(K$3=$F22,\"u\",\"\")","v":""},"","","","","","","","","",{"$f":"IF(U$3=$F22,\"u\",\"\")","v":""},"","","","","","","","","",{"$f":"IF(AE$3=$F22,\"u\",\"\")","v":""},"","","","","","",""]
[null,null,null,null,null,null,"",null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,"",null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,"",null,null,null,{"$f":"IF(K$3=$F25,\"u\",\"\")","v":""},"","","","","","","","","","","","","","","",{"$f":"IF(AA$3=$F25,\"u\",\"\")","v":""},"","","","","","","","","","",""]
[null,null,null,null,null,null,"",null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[null,null,null,null,null,null,"",null,null,null,{"$f":"IF(K$3=$F27,\"u\",\"\")","v":""},"","","","","","","","","",{"$f":"IF(U$3=$F27,\"u\",\"\")","v":""},"","","","","","","","","",{"$f":"IF(AE$3=$F27,\"u\",\"\")","v":""},"","","","","","",""]
[null,null,null,null,null,null,"",null,null,null,"","","","","","","","","","","","","","","","","","","","","","","","","","","",""]
[]
[]
[]
[]
[]
[]
[]
[null,null,"Members List:"]
[null,null,"Shuhan"]
[null,null,"Vittal"]
[null,null,"Jaya"]
[null,null,"Scott"]
[null,null,"Sam"]
[null,null,"Serena"]

{"sheet":"Sheet2","index":1,"n_rows":5,"n_cols":2,"rows_kept":5,"cut":false,"hidden":false,"merged":[]}
[null,"Statuses"]
[null,"Not started "]
[null,"In progress"]
[null,"Blocked"]
[null,"Complete"]